## Slide 1
SP ARIA // DETAILED RISK STRATEGY ROADMAP
SP Analytics Risk Intelligence Architecture · 24-Month Delivery Plan · Jun 2026 – May 2028
Phase 1 — Foundation
Phase 2 — Streaming Live
Phase 3 — Store Retirement
Phase 4 — Full Modernisation
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
Q1 2028
Q2 2028
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
TODAY
Migration
Symphony Non-PROD on Azure
AMER Prod miration (parallel run)
DataSynapse decommissioned
DR servers migrated
CycleCloud evaluation
MAPI Core lifts to Azure
⚑ Q3 2026
Kafka
sp-aria.rates.live (live curve)
File mounts decommissioned
Risk & Positions domain (Congo·TOS·MOSS)
Full EDP streaming · legacy pipelines retired
Migration
Structured products QA workers on Symphony
Mortgage workstream parallel run
EOD Risk / CCAR / FRTB on Symphony
DataSynapse fully retired
All batches live on Symphony
Symphony stable · CycleCloud PoC
Caching
Redis Enterprise L2 deployed
Coherence L2 decommissioned
Coherence 3-tier fully retired
Cache hit rate >95% validated
Full Redis+GridGain stable · zero file reads
SP
PostgreSQL: Beowulf config · scenario (SMT)
Azure SQL: risk results · cashflow store
MTG DBs decommissioned → ADLS Gen2
ADLS Gen2 Delta Lake · full audit trail
SP ARIA Data Store fully operational
On-Demand
Live curve in MAP (aria.rates.live)
Intraday <30 min · all products
FRTB intraday runs enabled
Full on-demand · sub-batch intraday
END 2026 — DECOMMISSION GATE
Azure HPC Migration
EDP Kafka Streaming
Symphony Migration
Redis + GridGain
SP ARIA Data Store
Intraday / On-Demand
Today (Jun 2026)
End-2026 Hard Gate